## 1. Risk Assessment
Step 1: Risk Identification |  | Step 2: Risk Assessment | [7 empty] | Step 3: Risk Management | [8 empty] | Step 4: Reviewed Level of Risk
Risk ID# | List of Possible Risks | Qualitative (Phase 1) |  |  | Quantitative (Phase 1) |  |  |  |  | What are we already doing about it? (Mitigating factors) | What more can we do about it? | Timescale | Person responsible | Estimated Total Cost of Control |  |  |  |  | Qualitative (Phase 2) |  |  | Quantitative (Phase 2)
|  | Likelihood (H/M/L) | Impact (H/M/L) | Initial Risk | AV | EF #1 | SLE #1 = (AV x EF) | ARO #1 | ALE #1 = (SLE x ARO) |  |  |  |  | Control ID# | Control Short Description | Upfront Costs | Annual Maintainence Costs | Annual TCO | Likelihood (H/M/L) | Impact (H/M/L) | Reviewed Risk | EF #2 | SLE #2 = (AV x EF#2) | ARO #2 | ALE #2 = (SLE#2 x ARO#2) | ROI | Is Control Financially Justified (Y/N)
1 | Identity theft | H | H | H | 17000000000 | 0.25% | 42500000 | 289 | 12282500000 | 1. Two Factor authentication with SMS based OTP. 2. Privacy control options to customers | 1. Replace SMS-based OTP with mobile-based authenticator app. (ex: Duo mobile, RSA Keys, Microsoft Authenticator). 2. Evaluate alternatives to Facebook single sign-on. 3. Enforce three-factor authentication. 4. Explore an alternate architecture to eliminate open API. | 1-6 months | CISO | 1.1 | Two Factor authentication with SMS based OTP | 5000000 | 1000000 | 6000000 | L | H | M | 0.1% | 17000000 | 100 | 1700000000 | 10576500000 | Y
[14 empty] | 1.2 | Privacy control options to customers | 1000000 | 500000 | 1500000 | M | M | M | 0.15% | 25500000 | 150 | 3825000000 | 8456000000 | Y
[14 empty] | 1.3 | Replace SMS-based OTP with mobile-based authenticator app. (ex: Duo mobile, RSA Keys, Microsoft Authenticator). | 10000000 | 3000000 | 13000000 | L | M | L | 0.1% | 17000000 | 60 | 1020000000 | 11249500000 | Y
[14 empty] | 1.4 | Evaluate alternatives to Facebook single sign-on. | 6000000 | 500000 | 6500000 | M | M | M | 0.2% | 34000000 | 200 | 6800000000 | 5476000000 | Y
[14 empty] | 1.5 | Enforce three-factor authentication. | 7000000 | 1000000 | 8000000 | L | M | L | 0.1% | 17000000 | 70 | 1190000000 | 11084500000 | Y
[14 empty] | 1.6 | Explore an alternate architecture to eliminate open API. | 20000000 | 5000000 | 25000000 | L | M | L | 0.1% | 17000000 | 60 | 1020000000 | 11237500000 | Y
2 | Financial theft | M | H | M - H | 50000000000 | 15% | 7500000000 | 0.02 | 150000000 | 1. All communication is encrypted using HTTPS. 2. AES 128 bit ciphers are used for encryption. 3. Adhering to all the best practices and regulations for corporations in the financial sector. 4. Fraud detection mechanism. | 1. Require one-time authentication code in P2P transcations 2. Explore controls and reporting processes to recover wrongly sent funds. | 3-12 months | CISO and CFO | 2.1 | All communication is encrypted using HTTPS. | 100000000 | 10000000 | 110000000 | L | M | L | 5% | 2500000000 | 0.01 | 25000000 | 15000000 | Y
[14 empty] | 2.2 | AES 128 bit ciphers are used for encryption. | 50000000 | 5000000 | 55000000 | L | M | L | 5% | 2500000000 | 0.01 | 25000000 | 70000000 | Y
[14 empty] | 2.3 | Adhere to all the best practices and regulations for corporations in the financial sector. | 5000000 | 2000000 | 7000000 | L | M | L | 7% | 3500000000 | 0.01 | 35000000 | 108000000 | Y
[14 empty] | 2.4 | Fraud detection mechanism. | 20000000 | 5000000 | 25000000 | L | M | L | 8% | 4000000000 | 0.01 | 40000000 | 85000000 | Y
[14 empty] | 2.5 | Require one-time authentication code in P2P transcations | 10000000 | 2000000 | 12000000 | L | M | L | 9% | 4500000000 | 0.01 | 45000000 | 93000000 | Y
[14 empty] | 2.6 | Explore controls and reporting processes to recover wrongly sent funds. | 25000000 | 5000000 | 30000000 | L | M | L | 15% | 7500000000 | 0.01 | 75000000 | 45000000 | Y
3 | Physical theft of hardware assets from the datacenter | L | H | M | 5000000000 | 70% | 3500000000 | 0.05 | 175000000 | 1. Physical security controls implemented at the datacenter. Eg: CCTV, Security personnel, Access controls 2. Redundant devices at disaster recovery site with data being backed up periodically. | 1. Reduce the backup periodicity as close to real-time as possible. | >1 year | Site Manager | 3.1 | Security Guard(s) throughout data center. | 1000 | 65000 | 66000 | L | M | L | 70% | 3500000000 | 0.02 | 70000000 | 104934000 | Y
[14 empty] | 3.2 | Physical Access System using biometric and ID standards. | 100000 | 200 | 100200 | L | L | L | 50% | 2500000000 | 0.02 | 50000000 | 124899800 | Y
[14 empty] | 3.3 | CCTV cameras throughout facility. | 45000 | 1500 | 46500 | L | L | L | 50% | 2500000000 | 0.03 | 75000000 | 99953500 | Y
[14 empty] | 3.4 | Reduce the backup periodicity as close to real-time as possible. | 25000 | 15000 | 40000 | L | M | M | 5% | 250000000 | 0.05 | 12500000 | 162460000 | Y
[14 empty] | 3.5 | Physical security controls implemented at the datacenter. Eg: CCTV, Security personnel, Access controls | 200000 | 50000 | 250000 | L | L | L | 50% | 2500000000 | 0.02 | 50000000 | 124750000 | Y
[14 empty] | 3.6 | Redundant devices at disaster recovery site with data being backed up periodically. | 750000 | 25000 | 775000 | L | L | L | 70% | 3500000000 | 0.05 | 175000000 | -775000 | N
[14 empty] | 3.7 | Encryption of data stored on hardware center. | 75000 | 25000 | 100000 | L | L | L | 35% | 1750000000 | 0.04 | 70000000 | 104900000 | Y
4 | Physical damage of assets in the datacenter | L | H | M | 5000000000 | 80% | 4000000000 | 0.001 | 4000000 | 1. Secure installation of all devices at the datacenters. 2. Specialized equipment to transport devices within the datacenter premises. 3. Fortified data centers with back-up power. 4. 24/7 security and monitoring team 5. RFID door access. | 1. Unmarked datacenter locations spread across different geographic locations. | >1 year | Site Manager | 4.1 | Secure installation of all devices at the datacenters. | 250000 | 100000 | 350000 | L | M | M | 40% | 2000000000 | 0.0005 | 1000000 | 2650000 | Y
[14 empty] | 4.2 | Specialized equipment to transport devices within the datacenter premises. | 200000 | 50000 | 250000 | L | M | M | 30% | 1500000000 | 0.0005 | 750000 | 3000000 | Y
[14 empty] | 4.3 | Fortified data centers with back-up power. | 5000000 | 500000 | 5500000 | L | L | L | 5% | 250000000 | 0.001 | 250000 | -1750000 | N
[14 empty] | 4.4 | 24/7 security and monitoring team | 1500000 | 250000 | 1750000 | L | M | M | 60% | 3000000000 | 0.0005 | 1500000 | 750000 | Y
[14 empty] | 4.5 | RFID door access. | 200000 | 25000 | 225000 | L | M | M | 50% | 2500000000 | 0.001 | 2500000 | 1275000 | Y
[14 empty] | 4.6 | Unmarked datacenter locations spread across different geographic locations. | 20000000 | 10000000 | 30000000 | L | L | L | 1% | 50000000 | 0.001 | 50000 | -26050000 | N
5 | Internal network outage | M | M | M | 2000000000 | 80% | 1600000000 | 3 | 4800000000 | 1. Network design that ensures that there are no single points of failure. 2. Use of routing and switching protocols with built-in failure recovery mechanisms. 3. Robust change management procedures that ensure that network changes are performed only outside of business hours etc. 4. Back-up power generators. | 1. Explore other technologies (hardware and software) that will make the network more resilient. 2. Build a disaster recovery site at a different location as a secondary HQ. | 1-2 years | Site Reliability Engineer | 5.1 | Network design that ensures that there are no single points of failure. | 1500000 | 50000 | 1550000 | L | L | L | 80% | 1600000000 | 1 | 1600000000 | 3198450000 | Y
[14 empty] | 5.2 | Use of routing and switching protocols with built-in failure recovery mechanisms. | 2000000 | 75000 | 2075000 | M | L | L | 30% | 600000000 | 3 | 1800000000 | 2997925000 | Y
[14 empty] | 5.3 | Explore other technologies (hardware and software) that will make the network more resilient. | 5000000 | 30000 | 5030000 | M | M | M | 50% | 1000000000 | 1 | 1000000000 | 3794970000 | Y
[14 empty] | 5.4 | Build a disaster recovery site at a different location as a secondary HQ. | 10000000 | 1000000 | 11000000 | L | L | L | 10% | 200000000 | 1 | 200000000 | 4589000000 | Y
[14 empty] | 5.5 | Robust change management procedures that ensure that network changes are performed only outside of business hours etc. | 10000 | 60000 | 70000 | M | M | M | 25% | 500000000 | 3 | 1500000000 | 3299930000 | Y
[14 empty] | 5.6 | Back-up power generators | 3000000 | 80000 | 3080000 | L | L | L | 5% | 100000000 | 2 | 200000000 | 4596920000 | Y
6 | Internet connectivity outage | M | M to H | M | 1200000000 | 50% | 600000000 | 4 | 2400000000 | 1. Backup internet service provider and automatic switchover mechanism between the two connections. 2. Disaster recovery site at a different geographical location with two separate internet connections. | 1. Explore alternate ISPs with better uptime statistics. | >1 year | Site Reliability Engineer, Network Engineer and ISP point-of-contact | 6.1 | Additional web servers to mitigate network congestion. | 900000 | 200000 | 1100000 | L | L | L | 45% | 540000000 | 1 | 540000000 | 1858900000 | Y
[14 empty] | 6.2 | Explore alternate ISPs with better uptime statistics. | 50 | 500 | 550 | L | M | M | 50% | 600000000 | 4 | 2400000000 | -550 | N
[14 empty] | 6.3 | Source internet link from multiple providers. | 750000 | 20000 | 770000 | L | L to M | L | 30% | 360000000 | 2.5 | 900000000 | 1499230000 | Y
[14 empty] | 6.4 | Backup internet service provider and automatic switchover mechanism between the two connections. | 500000 | 20000 | 520000 | L | L | L | 20% | 240000000 | 3 | 720000000 | 1679480000 | Y
[14 empty] | 6.5 | Disaster recovery site at a different geographical location with two separate internet connections. | 1000000 | 45000 | 1045000 | M | M | M | 5% | 60000000 | 0.5 | 30000000 | 2368955000 | Y
[14 empty] | 6.6 | Power surge protection. | 2000 | 50 | 2050 | M | M | M | 35% | 420000000 | 2.5 | 1050000000 | 1349997950 | Y
7 | Virus infection | H | H | H | 3000000000 | 80% | 2400000000 | 2 | 4800000000 | 1. IT department mandated anti-virus software installed on all the computers in the Venmo network. 2. Firewall is installed to prevent malware from entering the system. | 1. Venmo recommends mobile anti-virus applications to users. 2. Venmo partners with Mobile Security applications for free/discounted subscriptions to consumers. | < 1 year | Business Development Manager, CISO | 7.1 | IT department mandated anti-virus software installed on all the computers in the Venmo network. | 10000000 | 5000000 | 15000000 | L | L | L | 30% | 900000000 | 2 | 1800000000 | 2985000000 | Y
[14 empty] | 7.2 | Venmo recommends mobile anti-virus applications to users. | 10000 | 5000 | 15000 | M | M | M | 80% | 2400000000 | 2 | 4800000000 | -15000 | N
[14 empty] | 7.3 | Venmo partners with Mobile Security applications for free/discounted subscriptions to consumers. | 300000 | 1000 | 301000 | L | L to M | L | 50% | 1500000000 | 2 | 3000000000 | 1799699000 | Y
[14 empty] | 7.4 | Firewall is installed to prevent malware from entering the system. | 4000000 | 200000 | 4200000 | L | L | L | 40% | 1200000000 | 1 | 1200000000 | 3595800000 | Y
8 | Reduced consumer confidence due to lack of privacy protection | H | M | M - H | 17000000000 | 0.4% | 68000000 | 200 | 13600000000 | 1. Provide and allow customers to access policies of their data | 1. Allow options for customers to publicize their transactions 2. Provide transparency on the use of customers' personal data 3. Comply with data protection regislation such as the Gramm Leach Bliley Act (GLBA), California Consumer Privacy Act (CCPA), the US Federal Trade Commision (FTC) and the Fair Credit Reporting Act (FCRA) | < 6 months | CISO, Communications Team | 8.1 | Provide and allow customers to access policies of their data | 1000000 | 500000 | 1500000 | M | M | M | 0.4% | 68000000 | 150 | 10200000000 | 3398500000 | Y
[14 empty] | 8.2 | Allow options for customers to publicize their transactions | 4000000 | 500000 | 4500000 | L | M | L | 0.2% | 34000000 | 150 | 5100000000 | 8495500000 | Y
[14 empty] | 8.3 | Provide transparency on the use of customers' personal data | 2000000 | 300000 | 2300000 | L | M | L | 0.3% | 51000000 | 150 | 7650000000 | 5947700000 | Y
[14 empty] | 8.4 | Comply with data protection regislation such as the Gramm Leach Bliley Act (GLBA), California Consumer Privacy Act (CCPA), the US Federal Trade Commision (FTC) and the Fair Credit Reporting Act (FCRA) | 10000000 | 5000000 | 15000000 | L | M | L | 0.2% | 34000000 | 150 | 5100000000 | 8485000000 | Y
9 | System failures or interruptions due to natural disasters | L | H | M | 17000000000 | 30% | 5100000000 | 2 | 10200000000 | 1. Perform system upgrades and re-platform systems to improve reliability and speed. | 1. Maintain real-time backup data 2. Consider using cloud services to prevent data loss and unavailability 3. Use insurance plans to mitigate losses in the event of a natural disaster | < 1 year | CISO, Developer | 9.1 | Perform system upgrades and re-platform systems to improve reliability and speed. | 10000000 | 5000000 | 15000000 | L | M | L | 15% | 2550000000 | 2 | 5100000000 | 5085000000 | Y
[14 empty] | 9.2 | Maintain real-time backup data | 50000000 | 5000000 | 55000000 | L | M | L | 10% | 1700000000 | 2 | 3400000000 | 6745000000 | Y
[14 empty] | 9.3 | Consider using cloud services to prevent data loss and unavailability | 100000000 | 10000000 | 110000000 | L | M | L | 10% | 1700000000 | 2 | 3400000000 | 6690000000 | Y
[14 empty] | 9.4 | Use insurance plans to mitigate losses in the event of a natural disaster | 80000000 | 2000000 | 82000000 | M | L | L | 25% | 4250000000 | 2 | 8500000000 | 1618000000 | Y
10 | Losses due to transactions exchanged for illegal purposes | L | H | M | 50000000000 | 0.2% | 100000000 | 50 | 5000000000 | 1. Business usage has to be authorized via Venmo | 1. Provide seller and buyer protection 2. Collaborate with banks, agencies to set up anti-money laundering programs 3. Send customers warnings of unsual amounts or suspicious items/senders/buyers 4. Provide a hotline for users to report suspicious activities | < 1 year | CFO, CISO, Communications Team | 10.1 | Business usage has to be authorized via Venmo | 50000000 | 2000000 | 52000000 | L | M | L | 0.17% | 85000000 | 45 | 3825000000 | 1123000000 | Y
[14 empty] | 10.2 | Provide seller and buyer protection | 70000000 | 10000000 | 80000000 | M | L | L | 0.15% | 75000000 | 30 | 2250000000 | 2670000000 | Y
[14 empty] | 10.3 | Collaborate with banks, agencies to set up anti-money laundering programs | 80000000 | 10000000 | 90000000 | L | M | L | 0.1% | 50000000 | 30 | 1500000000 | 3410000000 | Y
[14 empty] | 10.4 | Send customers warnings of unsual amounts or suspicious items/senders/buyers | 60000000 | 15000000 | 75000000 | M | L | L | 0.18% | 90000000 | 30 | 2700000000 | 2225000000 | Y
[14 empty] | 10.5 | Provide a hotline for users to report suspicious activities | 60000 | 5000000 | 5060000 | M | L | L | 0.18% | 90000000 | 35 | 3150000000 | 1844940000 | Y
11 | Spearphising attempt on employees | M | H | M - H | 17000000000 | 40% | 6800000000 | 10 | 68000000000 | 1. Biannual security training sessions for all employees to keep them up-to-date on avoiding social engineering attempts. 2. Periodic test emails sent to random groups of employees to validate if they are clicking on suspicious links in emails with mandatory follow-up sessions for employees who click on the links. | 1. Organize periodic red team tests to aggressively determine weaknesses and avenues for spearphishing. | < 6 months | CISO, CEO, Human Resources, Internal Communications Department | 11.1 | Biannual security training sessions for all employees to keep them up-to-date on avoiding social engineering attempts. | 100000 | 50000 | 150000 | M | H | M | 10% | 1700000000 | 5 | 8500000000 | 59499850000 | Y
[14 empty] | 11.2 | Periodic test emails sent to random groups of employees to validate if they are clicking on suspicious links in emails with mandatory follow-up sessions for employees who click on the links. | 100000 | 25000 | 125000 | M | H | M | 10% | 1700000000 | 7 | 11900000000 | 56099875000 | Y
[14 empty] | 11.3 | Organize periodic red team tests to aggressively determine weaknesses and avenues for spearphishing. | 250000 | 100000 | 350000 | L | L | L | 7.5% | 1275000000 | 2 | 2550000000 | 65449650000 | Y
12 | Spyware Attack | M | M | M | 5000000000 | 40% | 2000000000 | 2 | 4000000000 | 1. All systems in venmo, Installed real-time anti spyware protection software. | 1. Deployment of DNS protection can be done to make venmo more secure from spywares | < 1 year | CISO and Business Developement Manager | 12.1 | Deployment of DNS protection can be done to make venmo more secure from spywares | 5000000 | 1000000 | 6000000 | L | L | L | 10% | 500000000 | 2 | 1000000000 | 2994000000 | Y
[14 empty] | 12.2 | All systems in venmo, Installed real-time anti spyware protection software. | 3000000 | 500000 | 3500000 | L | L | L | 20% | 1000000000 | 2 | 2000000000 | 1996500000 | Y
13 | Eavesdropping on network | M | H | M - H | 15000000000 | 75% | 11250000000 | 1 | 11250000000 | 1. Clock control is provided to ensure that no particular device remains active after a certian period of time and need to login again for accessing data, | 1. A thorough inspection by trained specialist can be done to keep check on user activity and devices | < 6 months | CISO, CFO | 13.1 | Clock control is provided to ensure that no particular device remains active after a certian period of time and need to login again for accessing data | 1500000 | 200000 | 1700000 | M | L | L | 30% | 4500000000 | 1 | 4500000000 | 6748300000 | Y
[14 empty] | 13.2 | A thorough inspection by trained specialist can be done to keep check on user activity and devices | 300000 | 400000 | 700000 | M | L | M | 50% | 7500000000 | 0.5 | 3750000000 | 7499300000 | Y
14 | Denial of Service | H | M | M - H | 2500000000 | 60% | 1500000000 | 4 | 6000000000 | 1. Backup servers and automatic switch over mechanism so that there is no issue in ongoing of work | 1. A web application firewall can be set up to prevent malicious code from being input. | < 1 year | CISO | 14.1 | A web application firewall can be set up to prevent malicious code from being input. | 4000000 | 2500000 | 6500000 | L | L | L | 30% | 750000000 | 3 | 2250000000 | 3743500000 | Y
[14 empty] | 14.2 | Backup servers and automatic switch over mechanism so that there is no issue in ongoing of work | 3500000 | 500000 | 4000000 | L | M | M | 20% | 500000000 | 2 | 1000000000 | 4996000000 | Y
15 | Source address spoofing on customers (*) | M | M | M | 110 | 20% | 22 | 150000 | 3300000 | 1. Use of HTTPS, requiring digital certificate signed by Certifying Authority. 2. Limiting non-mobile web application functionality | 1. Prevent venmo from operating on public wifi networks | 1-3 months | CISO | 15.1 | Use of HTTPS, requiring digital certificate signed by Certifying Authority. | 50 | 5 | 55 | M | L to M | L | 2% | 2.2 | 100 | 220 | 3299725 | Y
[14 empty] | 15.2 | Limiting non-mobile web application functionality | 700 | 100 | 800 | L | M | L to M | 10% | 11 | 75000 | 825000 | 2474200 | Y
[14 empty] | 15.3 | Prevent venmo from operating on public wifi networks | 500 | 5 | 505 | L | L | L | 15% | 16.5 | 50000 | 825000 | 2474495 | Y
16 | Terminated Employee releases PII | L | M to H | H | 17000000000 | 100% | 17000000000 | 0.1 | 1700000000 | 1. Immediate revoked access of terminated employee. 2. Implementation of access privilege levels. 3. Separation of Duties | 1. Procedure to revoke access prior to official termination notification. | 1-3 months | CEO, CISO, Human Resources | 16.1 | Immediate revoked access of terminated employee. | 5 | 5000 | 5005 | L | L | L | 0% | 0 | 0.05 | 0 | 1699994995 | Y
[14 empty] | 16.2 | Implementation of access privilege levels. | 15000 | 100000 | 115000 | L | M | M | 20% | 3400000000 | 0.05 | 170000000 | 1529885000 | Y
[14 empty] | 16.3 | Separation of Duties | 10000 | 150000 | 160000 | L | M | M | 20% | 3400000000 | 0.05 | 170000000 | 1529840000 | Y
[14 empty] | 16.4 | Procedure to revoke access prior to official termination notification. | 200 | 300 | 500 | L | L | L | 0% | 0 | 0.01 | 0 | 1699999500 | Y
17 | Employee downloads malware from non-work related websites | M | M | M | 5000 | 60% | 3000 | 500 | 1500000 | 1. Anti-virus software 2. Intrusion prevention/detection system (IPS/IDS) 3. Data Encryption 4. Data Backup | 1. Create a policy that employees cannot access non-work-related websites. 2. Implement penalties for employees who violate this policy. 3. Implement website blocking software. | < 1 year | CISO, CEO, Human Resources, Internal Communications Department | 17.1 | Anti-virus software | 100000 | 500000 | 600000 | L | L | L | 20% | 1000 | 100 | 100000 | 800000 | Y
[14 empty] | 17.2 | Intrusion prevention/detection system (IPS/IDS) | 50000 | 65000 | 115000 | L | L | L | 35% | 1750 | 100 | 175000 | 1210000 | Y
[14 empty] | 17.3 | Data Encryption | 50000 | 20000 | 70000 | L | L to M | L | 10% | 500 | 500 | 250000 | 1180000 | Y
[14 empty] | 17.4 | Data Backup | 700000 | 250000 | 950000 | M | L to M | M | 45% | 2250 | 500 | 1125000 | -575000 | N
[14 empty] | 17.5 | Create a policy that employees cannot access non-work-related websites. | 5000 | 8000 | 13000 | L | M | L to M | 10% | 500 | 25 | 12500 | 1474500 | Y
[14 empty] | 17.6 | Implement penalties for employees who violate policy on non-work related websites. | 5000 | 8000 | 13000 | M | L | L to M | 5% | 250 | 10 | 2500 | 1484500 | Y
[14 empty] | 17.7 | Implement website blocking software. | 50000 | 20000 | 70000 | L | L | L | 5% | 250 | 3 | 750 | 1429250 | Y
18 | Change to network configuration that would result in non-compliance of regulations | H | H | H | 2000000000 | 20% | 400000000 | 1 | 400000000 | 1. Rigorous change management process with prior approval required from at least two senior leaders. | 1. Automated compliance monitoring software that detects any changes that will put the network out of compliance and prevent the change from being committed without administrative approval. | > 1 year | CISO, Network Operations Team, DevOps | 18.1 | Rigorous change management process with prior approval required from at least two senior leaders. | 10000 | 60000 | 70000 | L | M | M | 20% | 400000000 | 0.1 | 40000000 | 359930000 | Y
[14 empty] | 18.2 | Automated compliance monitoring software that detects any changes that will put the network out of compliance and prevent the change from being committed without administrative approval. | 250000 | 50000 | 300000 | M | M | M | 10% | 200000000 | 0.1 | 20000000 | 379700000 | Y
19 | Software vulnerability discovered by a bad actor | M | H | M | 50000000000 | 25% | 12500000000 | 2 | 25000000000 | 1. All development follows the SDLC process which involves a detailed testing phase to detect vulnerabilities. 2. QA team keeps updating its test procedures and modules to meet or exceed industry best practices. | 1. Incorporate more open-source software so that intelligence from the open source community can be used to detect and fix vulnerabilities faster. | 1-2 years | CISO, CEO, Engineering team | 19.1 | All development follows the SDLC process which involves a detailed testing phase to detect vulnerabilities. | 100000 | 20000 | 120000 | L | M | L | 15% | 7500000000 | 0.01 | 75000000 | 24924880000 | Y
[14 empty] | 19.2 | QA team keeps updating its test procedures and modules to meet or exceed industry best practices. | 500000 | 150000 | 650000 | L | M | L | 15% | 7500000000 | 0.01 | 75000000 | 24924350000 | Y
[14 empty] | 19.3 | Incorporate more open-source software so that intelligence from the open source community can be used to detect and fix vulnerabilities faster. | 2000000 | 200000 | 2200000 | L | L | L | 10% | 5000000000 | 0.001 | 5000000 | 24992800000 | Y
20 | Installation of the Venmo app on an unpatched device | H | H | H | 50000000000 | 50% | 25000000000 | 0.1 | 2500000000 | 1. Working with mobile platform providers (Google, Apple) to prevent the app from installing unless it is on a minimum version number. | 1. Engineer the app to run in a sandboxed environment irrespective of the mobile platform it is installed on. | 2 years | CISO, CEO, Engineering team | 20.1 | Working with mobile platform providers (Google, Apple) to prevent the app from installing unless it is on a minimum version number. | 10000000 | 100000 | 10100000 | M | M | M | 5% | 2500000000 | 0.001 | 2500000 | -12600000 | N
[14 empty] | 20.2 | Engineer the app to run in a sandboxed environment irrespective of the mobile platform it is installed on. | 5000000 | 1500000 | 6500000 | L | L | L | 5% | 2500000000 | 0.0001 | 250000 | -6750000 | N
(*) | For Risk#15, AV was guestimated based on black market value of credit card PII for one customer. This because the spoofing attack would target individual customers.
# | References:
1 | Bloomenthal, Andrew. (2020, March 5). How safe is Venmo and is it free?. Investopedia. https://www.investopedia.com/articles/personal-finance/032415/how-safe-venmo-and-why-it-free.asp.
2 | FTC announces settlement for Venmo’s alleged violations of the GLBA’s privacy and safeguard rules. (2018, March 2). Retrieved March 27, 2020, from https://www.huntonprivacyblog.com/2018/03/02/ftc-announces-settlement-for-venmos-alleged-violations-of-the-glbas-privacy-and-safeguards-rules/.
3 | Jr., T. H. (2018, July 26). How these billion-dollar businesses started as happy accidents and side gigs. Retrieved March 27, 2020, from https://www.cnbc.com/2018/07/26/how-billion-dollar-companies-from-facebook-to-venmo-got-started.html.
4 | Posey, Brian. (2012, February 23). 10 ways to avoid costly PCI compliance violations. TechRepublic. https://www.techrepublic.com/blog/10-things/10-ways-to-avoid-costly-pci-compliance-violations/.
5 | Rudegeair, P. (2018, November 24). Venmo takes losses after payments fraud. Retrieved March 27, 2020, from https://www.marketwatch.com/story/venmo-takes-losses-after-payments-fraud-2018-11-24.
6 | Stack, Brian. (2017, December 6). Here’s how much your personal information is selling for on the dark web. Experian. https://www.experian.com/blogs/ask-experian/heres-how-much-your-personal-information-is-selling-for-on-the-dark-web/.

## 2. Countermeasures
Risk Id# | Risk ID # | Risk Identification | Control ID # | Control | A. Control Category |  |  | B. Control Classification
[5 empty] | Technical | Administrative | Physical | Preventive | Detective | Corrective | Deterrent | Recovery | Compensating | Directive
1 | 1 | Identity Theft | 1.1 | Two Factor authentication with SMS based OTP | x |  |  | x |  |  | x
|  |  | 1.2 | Privacy control options to customers | x |  |  | x | [5 empty] | x
|  |  | 1.3 | Replace SMS-based OTP with mobile-based authenticator app. (ex: Duo mobile, RSA Keys, Microsoft Authenticator). | x |  |  | x |  |  | x
|  |  | 1.4 | Evaluate alternatives to Facebook single sign-on. | x |  |  | x
|  |  | 1.5 | Enforce three-factor authentication. | x |  |  | x |  |  | x
|  |  | 1.6 | Explore an alternate architecture to eliminate open API. | x |  |  | x
2 | 2 | Financial Theft | 2.1 | All communication is encrypted using HTTPS. | x |  |  | x |  |  | x
|  |  | 2.2 | AES 128 bit ciphers are used for encryption. | x |  |  | x |  |  | x
|  |  | 2.3 | Adhere to all the best practices and regulations for corporations in the financial sector. |  | x |  | x | [5 empty] | x
|  |  | 2.4 | Fraud detection mechanism. |  | x |  |  | x
|  |  | 2.5 | Require one-time authentication code in P2P transcations | x |  |  | x |  |  | x
|  |  | 2.6 | Explore controls and reporting processes to recover wrongly sent funds. |  | x | [5 empty] | x | x
3 | 3 | Physical theft of hardware assets from the datacenter | 3.1 | Security Guard(s) throughout data center. |  |  | x | x |  |  | x
|  |  | 3.2 | Physical Access System using biometric and ID standards. | x |  | x | x | x |  | x
|  |  | 3.3 | CCTV cameras throughout facility. | x |  | x | x | x |  | x | x
|  |  | 3.4 | Reduce the backup periodicity as close to real-time as possible. | x |  |  | x |  |  |  | x
|  |  | 3.5 | Physical security controls implemented at the datacenter. Eg: CCTV, Security personnel, Access controls | x |  | x | x | x |  | x | x
|  |  | 3.6 | Redundant devices at disaster recovery site with data being backed up periodically. | x |  | x |  |  |  |  | x | x
|  |  | 3.7 | Encryption of data stored on hardware center. | x |  |  | x |  |  |  |  | x
| 4 | Physical damage of assets in the datacenter | 4.1 | Secure installation of all devices at the datacenters. |  |  | x | x
|  |  | 4.2 | Specialized equipment to transport devices within the datacenter premises. |  |  | x | x
|  |  | 4.3 | Fortified data centers with back-up power. | x | x |  | x |  | x
|  |  | 4.4 | 24/7 security and monitoring team | x |  |  | x | x |  | x
|  |  | 4.5 | RFID door access. | x
|  |  | 4.6 | Unmarked datacenter locations spread across different geographic locations. | x | x |  |  |  | x |  | x
| 5 | Internal network outage | 5.1 | Network design that ensures that there are no single points of failure. | x | x |  | x
|  |  | 5.2 | Use of routing and switching protocols with built-in failure recovery mechanisms. |  | x | x | x |  |  |  | x
|  |  | 5.3 | Robust change management procedures that ensure that network changes are performed only outside of business hours etc. |  |  |  | x
|  |  | 5.4 | Back-up power generators |  |  | x |  |  | x |  | x | x
| 6 | Internet connectivity outage | 6.1 | Additional web servers to mitigate network congestion. | x |  |  | x |  | x |  |  | x
|  |  | 6.2 | Explore alternate ISPs with better uptime statistics. |  | x |  | x
|  |  | 6.3 | Source internet link from multiple providers. | x |  |  | x |  |  |  | x | x
|  |  | 6.4 | Backup internet service provider and automatic switchover mechanism between the two connections. | x |  |  | x |  | x |  | x
|  |  | 6.5 | Disaster recovery site at a different geographical location with two separate internet connections. | x |  | x |  |  | x |  | x | x
|  |  | 6.6 | Power surge protection. |  |  | x | x
| 7 | Virus infection | 7.1 | IT department mandated anti-virus software installed on all the computers in the Venmo network. | x |  |  | x
|  |  | 7.2 | Firewall is installed to prevent malware from entering the system. | x |  |  | x
| 8 | Reduced consumer confidence due to lack of privacy protection | 8.1 | Provide and allow customers to access policies of their data |  | x |  | x | [5 empty] | x
|  |  | 8.2 | Allow options for customers to publicize their transactions |  | x |  | x | [5 empty] | x
|  |  | 8.3 | Provide transparency on the use of customers' personal data |  | x |  | x
|  |  | 8.4 | Comply with data protection regislation such as the Gramm Leach Bliley Act (GLBA), California Consumer Privacy Act (CCPA), the US Federal Trade Commision (FTC) and the Fair Credit Reporting Act (FCRA) |  | x |  | x
| 9 | System failures or interruptions due to natural disasters | 9.1 | Perform system upgrades and re-platform systems to improve reliability and speed | x |  |  |  |  | x
|  |  | 9.2 | Maintain real-time backup data | x |  |  | x |  |  |  | x
|  |  | 9.3 | Consider using cloud services to prevent data loss and unavailability | x |  |  |  |  | x |  | x
|  |  | 9.4 | Use insurance plans to mitigate losses in the event of a natural disaster |  | x | [6 empty] | x
| 10 | Losses due to transactions exchanged for illegal purposes | 10.1 | Business usage has to be authorized via Venmo
|  |  | 10.2 | Provide seller and buyer protection
|  |  | 10.3 | Collaborate with banks, agencies to set up anti-money laundering programs
|  |  | 10.4 | Send customers warnings of unsual amounts or suspicious items/senders/buyers
|  |  | 10.5 | Provide a hotline for users to report suspicious activities
| 11 | Spearphising attempt on employees | 11.1 | Biannual security training sessions for all employees to keep them up-to-date on avoiding social engineering attempts. |  | x |  | x |  |  | x
|  |  | 11.2 | Periodic test emails sent to random groups of employees to validate if they are clicking on suspicious links in emails with mandatory follow-up sessions for employees who click on the links. | x | x |  | x |  |  | x
|  |  | 11.3 | Organize periodic red team tests to aggressively determine weaknesses and avenues for spearphishing. | x |  |  | x
| 12 | Spyware Attack | 12.1 | All systems in venmo, Installed real-time anti spyware protection software. | x |  |  | x |  |  | x
| 13 | Eavesdropping on network | 13.1 | Clock control is provided to ensure that no particular device remains active after a certian period of time and need to login again for accessing data |  |  |  | x
| 14 | Denial of Service | 14.1 | Backup servers and automatic switch over mechanism are present so that there is no issue in ongoing of work |  |  | x |  |  |  |  | x
| 15 | Spoofing | 15.1 | Use of HTTPS, requiring digital certificate signed by Certifying Authority. | x |  |  | x | x
|  |  | 15.2 | Limiting non-mobile web application functionality | x |  |  | x | [5 empty] | x
|  |  | 15.3 | Prevent venmo from operating on public wifi networks | x |  |  | x
| 16 | Terminated Employee releases PII | 16.1 | Immediate revoked access of terminated employee. |  | x |  | x | [5 empty] | x
|  |  | 16.2 | Implementation of access privilege levels. | x | x |  | x | x
|  |  | 16.3 | Separation of Duties |  | x |  | x | [5 empty] | x
|  |  | 16.4 | Procedure to revoke access prior to official termination notification. |  | x |  | x | [5 empty] | x
| 17 | Employee downloads malware from non-work related websites | 17.1 | Anti-virus software | x |  |  | x | x | x |  | x
|  |  | 17.2 | Intrusion prevention/detection system (IPS/IDS) | x |  |  | x | x
|  |  | 17.3 | Data Encryption | x |  |  | x |  |  |  |  | x
|  |  | 17.4 | Data Backup | x |  |  | x |  |  |  | x
|  |  | 17.5 | Create a policy that employees cannot access non-work-related websites. |  | x |  | x |  |  | x |  |  | x
|  |  | 17.6 | Implement penalties for employees who violate this policy. |  | x |  |  |  | x | x |  | x
|  |  | 17.7 | Implement website blocking software. | x |  |  | x | x | x | x
| 18 | Change to network configuration that would result in non-compliance of regulations | 18.1 | Rigorous change management process with prior approval required from at least two senior leaders. |  | x |  | x | x |  | x |  |  | x
|  |  | 18.2 | Automated compliance monitoring software that detects any changes that will put the network out of compliance and prevent the change from being committed without administrative approval. | x |  |  | x | x |  | x | x
| 19 | Software vulnerability discovered by a bad actor | 19.1 | All development follows the SDLC process which involves a detailed testing phase to detect vulnerabilities. |  | x |  | x |  |  | x |  |  | x
|  |  | 19.2 | QA team keeps updating its test procedures and modules to meet or exceed industry best practices. | x |  |  | x |  | x | x
|  |  | 19.3 | Incorporate more open-source software so that intelligence from the open source community can be used to detect and fix vulnerabilities faster. | x |  |  | x |  | x | x
| 20 | Installation of the Venmo app on an unpatched device | 20.1 | Working with mobile platform providers (Google, Apple) to prevent the app from installing unless it is on a minimum version number. | x | x |  | x |  |  | x |  |  | x
|  |  | 20.2 | Engineer the app to run in a sandboxed environment irrespective of the mobile platform it is installed on. | x |  |  | x